## Sheet1
| User Story | Time Allocated
WEEK - 1 | D1 Designing basic GUI for main screen. Create "Start screen capture" button, Create "Stop screen capture" button. Create a JList having a list of timing intervals(2,3,4,5..) D2 UI styling(making the background black and add images instead of start and stop text) | D1 - D2-
| D1 Write code to ensure that when the start button is being clicked, the app minimizes to the taskbar automatically. D2 Code to ensure the restore functionality of the main window. | D1 - D2-
| D1 Implement logic to start screen capture when "Start" is clicked using java.awt.Robot D2 Add functionality for "Stop screen capture" to stop the screenshot process. | D1 - D2-
| D1,D2 Ensure that the screenshot is being captured in regular intervals. Ensure the application minimizes to the task manager during capture. | D1 - D2-
| D1,D2 Write code to manage temporary screenshot storage. Assign unique filenames. | D1 - D2-
D1 ,D2 Integration of Start and Stop buttons together.(bug fixing)
Bug fixing
WEEK-2 | D1,D2 When the stop button is clicked,stop the screenshot process.
D1 When the stop button is clicked, make sure that all the captured screenshots are taken from the temportary folder and is stored in a collection(BufferedImage). D2 From the collection take the image objects and load into a new window(Preview window).
D1 Ensure that each screenshot has a checkbox for selection. D2 Enhance the GUI to display screenshots in a grid layout with checkboxes.
D1 Add "Save" button under the preview window. D2 Logic to understand what all images are selected based on checkbox states.
Integration and testing the application.
WEEK-3 | D1 Use iText export selected screenshots into a PDF. D2 Code to ensure all screenshots are displayed in order within the PDF.
D1,D2 Implementing "Save" button When save button is clicked, open a file-saving dialog box for selecting the PDF save location.
D1 Clearing all the screenshots from the temporary location after saving the PDF. D2 Close the main window and preview window.
Converting into desktop application.
Documentation.